## Slide 1: Chapter 5 - Software effort estimation
SOFTWARE
PROJECT MANAGEMENT

## Slide 2: What makes a successful project?
BUT what if the targets are not achievable?
Delivering:
  Agreed functionality on time
  At the agreed cost with the required quality
Stages:
1. Set targets
2. Attempt to achieve targets
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 3: Some problems with estimating
Subjective nature of much of estimating
  It may be difficult to produce evidence to support your precise target
Political pressures
  Managers may wish to reduce estimated costs in order to win support for acceptance of a project proposal
Changing technologies
  these bring uncertainties, especially in the early days when there is a ‘learning curve’
Projects differ
  Experience on one project may not be applicable to another
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 4: Over and under-estimating
Parkinson’s Law: ‘Work expands to fill the time available’
An over-estimate is likely to cause project to take longer than it would otherwise
Weinberg’s Zeroth Law of reliability: ‘a software project that does not have to meet a reliability requirement can meet any other requirement’
4
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 5: Basis for successful estimating
Information about past projects
  Need to collect performance details about past project: how big were they? How much effort/time did they need?
Need to be able to measure the amount of work involved
  Traditional size measurement for software is ‘lines of code’ – but this can have problems
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 6: A taxonomy of estimating methods
Bottom-up - activity based, analytical
Parametric or algorithmic models e.g. function points
Expert opinion - just guessing?
Analogy - case-based, comparative
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 7: Bottom-up versus top-down
Bottom-up
use when no past project data
  identify all tasks that have to be done – so quite time-consuming
  use when you have no data about similar past projects
Top-down
  produce overall estimate based on project cost drivers
  based on past project data
  divide overall estimate between jobs to be done
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 8: Bottom-up estimating
1. Break project into smaller and smaller components
[2. Stop when you get to what one person can do in one/two weeks]
3. Estimate costs for the lowest level activities
4. At each higher level calculate estimate by adding estimates for lower levels
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 9: Top-down estimates
Produce overall estimate using effort driver(s)
distribute proportions of overall estimate to components
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 10: Algorithmic/Parametric models
COCOMO (lines of code) and function points examples of these
Problem with COCOMO etc:
But what is desired is
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 11: Parametric models - the need for historical data
simplistic model for an estimate
  estimated effort = (system size) / productivity
e.g.
  system size = lines of code
  productivity = lines of code per day
productivity = (system size) / effort
  based on past projects
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 12: Parametric models
Some models focus on task or system size e.g. Function Points
FPs originally used to estimate Lines of Code, rather than effort
model
Number of file types
Numbers of input and output transaction types
System size
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 13: Parametric models
Other models focus on productivity: e.g. COCOMO
Lines of code (or FPs etc) an input
System size
Productivity factors
Estimated effort
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 14: Expert judgement
Asking someone who is familiar with and knowledgeable about the application area and the technologies to provide an estimate
Particularly appropriate where existing code is to be modified
Research shows that experts judgement in practice tends to be based on analogy
Attribute values effort
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 15: Estimating by analogy
attribute values | effort
attribute values | effort
attribute values | effort
attribute values | effort
attribute values | effort
attribute values | effort
source cases
attribute values | ?????
Select case with closet attribute values
target cases
Use effort from source as estimate
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 16: Stages: identify
Significant features of the current project
previous project(s) with similar features
differences between the current and previous projects
possible reasons for error (risk)
measures to reduce uncertainty
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 17: Machine assistance for source selection (ANGEL)
Euclidean distance = sq root ((lt-ls)2 + (Ot-Os)2 )
Number of outputs
Number of inputs
Source A
Source B
target
Ot-Os
lt-ls
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 18: Parametric models
We are now looking more closely at four parametric models:
  Albrecht/IFPUG function points
  Symons/Mark II function points
  COSMIC function points
  COCOMO81 and COCOMO II
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 19: Albrecht/IFPUG function points
Albrecht worked at IBM and needed a way of measuring the relative productivity of different programming languages.
Needed some way of measuring the size of an application without counting lines of code.
Identified five types of component or functionality in an information system
Counted occurrences of each type of functionality in order to get an indication of the size of an information system
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 20: Albrecht/IFPUG function points
Five function types:
  Logical interface file (LIF) types – equates roughly to a datastore in systems analysis terms. Created and accessed by the target system
  External interface file types (EIF) – where data is retrieved from a datastore which is actually maintained by a different application
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 21: Albrecht/IFPUG function points
  External input (EI) types – input transactions which update internal computer files
  External output (EO) types – transactions which extract and display data from internal computer files. Generally involves creating reports.
  External inquiry (EQ) types – user initiated transactions which provide information but do not update computer files. Normally the user inputs some data that guides the system to the information the user needs
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 22: Albrecht complexity multipliers
External user types | Low complexity | Medium complexity | High complexity
EI | 3 | 4 | 6
EO | 4 | 5 | 7
EQ | 3 | 4 | 6
LIF | 7 | 10 | 15
EIF | 5 | 7 | 10
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 23: Examples
Payroll application has:
  Transaction to input, amend and delete employee details – an EI that is rated of medium complexity
  A transaction that calculates pay details from timesheet data that is input – an EI of high complexity
  A transaction of medium complexity that prints out pay-to-date details for each employee – EO
  A file of payroll details for each employee – assessed as of medium complexity LIF
  A personnel file maintained by another system is accessed for name and address details – a simple EIF
What would be the FP counts for these?
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 24: FP counts
Medium EI 4 FPs
High complexity EI 6 FPs
Medium complexity EO 5 FPs
Medium complexity LIF 10 FPs
Simple EIF 5 FPs
Total 30 FPs
If previous projects delivered 5 FPs a day, implementing the above should take 30/5 = 6 days
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 25: Function points Mark II
Developed by Charles R. Symons
‘Software sizing and estimating - Mk II FPA’, Wiley & Sons, 1991.
Builds on work by Albrecht
Work originally for CCTA:
  should be compatible with SSADM; mainly used in UK
has developed in parallel to IFPUG FPs
A simpler method
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 26: Function points Mk II
For each transaction, count
  data items input (Ni )
  data items output (N0)
  entity types accessed (Ne)
FP count = Ni * 0.58 + Ne * 1.66 + N0 * 0.26
#entities accessed
#input items
#output items
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 27: Function points for embedded systems
Mark II function points, IFPUG function points were designed for information systems environments
COSMIC FPs attempt to extend concept to embedded systems
Embedded software seen as being in a particular ‘layer’ in the system
Communicates with other layers and also other components at same level
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 28: Layered software
Receives request
Supplies service
Makes a request for a service
Receives service
Receives storage
peer component
Software component
Higher layers
Lower layers
Data reads/ writes
Peer to peer communication
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 29: COSMIC FPs
The following are counted:
  Entries: movement of data into software component from a higher layer or a peer component
  Exits: movements of data out
  Reads: data movement from persistent storage
  Writes: data movement to persistent storage
Each counts as 1 ‘COSMIC functional size unit’ (Cfsu)
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 30: COCOMO81
Based on industry productivity standards - database is constantly updated
Allows an organization to benchmark its software development productivity
Basic model
effort = c x size k
C and k depend on the type of system: organic, semi-detached, embedded
Size is measured in ‘kloc’ ie. Thousands of lines of code
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 31: The COCOMO constants
System type | C | K
Organic (broadly, information systems) | 2.4 | 1.05
Semi-detached | 3.0 | 1.12
Embedded (broadly, real-time) | 3.6 | 1.20
k exponentiation – ‘to the power of…’
adds disproportionately more effort to the larger projects
takes account of bigger management overheads
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 32: Development effort multipliers (dem)
According to COCOMO, the major productivity drivers include:
  Product attributes: required reliability, database size, product complexity
  Computer attributes: execution time constraints, storage constraints, virtual machine (VM) volatility
  Personnel attributes: analyst capability, application experience, VM experience, programming language experience
  Project attributes: modern programming practices, software tools, schedule constraints:
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 33: Using COCOMO development effort multipliers (dem)
An example: for analyst capability:
  Assess capability as very low, low, nominal, high or very high
  Extract multiplier:
  very low 1.46
  low 1.19
  nominal 1.00
  high 0.80
  very high 0.71
  Adjust nominal estimate e.g. 32.6 x 0.80 = 26.8 staff months
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 34: COCOMO II
An updated version of COCOMO:
  There are different COCOMO II models for estimating at the ‘early design’ stage and the ‘post architecture’ stage when the final system is implemented. We’ll look specifically at the first.
  The core model is:
  pm = A(size)(sf) ×(em1) ×(em2) ×(em3)….
  where pm = person months, A is 2.94, size is number of thousands of lines of code, sf is the scale factor, and em is an effort multiplier
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 35: COCOMO II Scale factor
Based on five factors which appear to be particularly sensitive to system size
Precedentedness (PREC). Degree to which there are past examples that can be consulted
Development flexibility (FLEX). Degree of flexibility that exists when implementing the project
Architecture/risk resolution (RESL). Degree of uncertainty about requirements
Team cohesion (TEAM).
Process maturity (PMAT) could be assessed by CMMI – see Section 13.8
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 36: COCOMO II Scale factor values
Driver | Very low | low | Nom-inal | High | Very high | Extra high
PREC | 6.20 | 4.92 | 3.72 | 2.48 | 1.24 | 0.00
FLEX | 5.07 | 4.05 | 3.04 | 2.03 | 1.01 | 0.00
RESL | 7.07 | 5.65 | 4.24 | 2.83 | 1.41 | 0.00
TEAM | 5.48 | 4.38 | 3.29 | 2.19 | 1.10 | 0.00
PMAT | 7.80 | 6.24 | 4.68 | 3.12 | 1.56 | 0.00
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 37: Example of scale factor
A software development team is developing an application which is very similar to previous ones it has developed.
A very precise software engineering document lays down very strict requirements. PREC is very high (score 1.24).
FLEX is very low (score 5.07).
The good news is that these tight requirements are unlikely to change (RESL is high with a score 2.83).
The team is tightly knit (TEAM has high score of 2.19), but processes are informal (so PMAT is low and scores 6.24)
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 38: Scale factor calculation
The formula for sf is
sf = B + 0.01× Σ scale factor values
i.e. sf = 0/91 + 0.01
× (1.24 + 5.07 + 2.83 + 2.19 + 6.24)
= 1.0857
If system contained 10 kloc then estimate would be 2.94 x 101.0857 = 35.8 person months
Using exponentiation (‘to the power of’) adds disproportionately more to the estimates for larger applications
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 39: Effort multipliers
As well as the scale factor effort multipliers are also assessed:
  RCPX Product reliability and complexity
  RUSE Reuse required
  PDIF Platform difficulty
  PERS Personnel capability
  FCIL Facilities available
  SCED Schedule pressure
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 40: Effort multipliers
 | Extra low | Very low | low | Nom-inal | High | Very high | Extra high
RCPX | 0.49 | 0.60 | 0.83 | 1.00 | 1.33 | 1.91 | 2.72
RUSE |  |  | 0.95 | 1.00 | 1.07 | 1.15 | 1.24
PDIF |  |  | 0.87 | 1.00 | 1.29 | 1.81 | 2.61
PPERS | 2.12 | 1.62 | 1.26 | 1.00 | 0.83 | 0.63 | 0.50
PREX | 1.59 | 1.33 | 1.12 | 1.00 | 0.87 | 0.74 | 0.62
FCIL | 1.43 | 1.30 | 1.10 | 1.00 | 0.87 | 0.73 | 0.62
SCED |  | 1.43 | 1.14 | 1.00 | 1.00 | 1.00 | 
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 41: Example
Say that a new project is similar in most characteristics to those that an organization has been dealing for some time:
except:
  the software to be produced is exceptionally complex and will be used in a safety critical system.
  The software will interface with a new operating system that is currently in beta status.
  To deal with this the team allocated to the job are regarded as exceptionally good, but do not have a lot of experience on this type of software.
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 42: Example
RCPX very high 1.91
PDIF very high 1.81
PERS extra high 0.50
PREX nominal 1.00
All other factors are nominal
Say estimate is 35.8 person months
With effort multipliers this becomes 35.8 x 1.91 x 1.81 x 0.5 = 61.9 person months
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 43: Some conclusions: how to review estimates
Ask the following questions about an estimate
  What are the task size drivers?
  What productivity rates have been used?
  Is there an example of a previous project of about the same size?
  Are there examples of where the productivity rates used have actually been found?
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course