## Slide 1: Chapter 6 - Activity planning
SOFTWARE
PROJECT MANAGEMENT

## Slide 2: Scheduling
‘Time is nature’s way of stopping everything happening at once’
Having
  worked out a method of doing the project
  identified the tasks to be carried
  assessed the time needed to do each task need to allocate dates/times for the start and end of each activity
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 3: Activity networks
These help us to:
  Assess the feasibility of the planned project completion date
  Identify when resources will need to be deployed to activities
  Calculate when costs will be incurred
This helps the co-ordination and motivation of the project team
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 4: Defining activities
Activity networks are based on some assumptions:
A project is:
  Composed of a number of activities
  May start when at least one of its activities is ready to start
  Completed when all its activities are completed
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 5: Defining activities
An activity
  Must have clearly defined start and end-points
  Must have resource requirements that can be forecast: these are assumed to be constant throughout the project
  Must have a duration that can be forecast
  May be dependent on other activities being completed first (precedence networks)
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 6: Identifying activities
Work-based: draw-up a Work Breakdown Structure listing the work items needed
Product-based approach
  list the deliverable and intermediate products of project – product breakdown structure (PBS)
  Identify the order in which products have to be created
  work out the activities needed to create the products
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 7: Hybrid approach
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 8: The final outcome of the planning process
A project plan as a bar chart
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 9: PERT vs cpm
Do B
Do C
Do A
Do D
Do A
Do B
Do C
Do D
CPM
PERT
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 10: Drawing up a PERT diagram
No looping back is allowed – deal with iterations by hiding them within single activities
milestones – ‘activities’, such as the start and end of the project, which indicate transition points. They have zero duration.
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 11: Lagged activities
where there is a fixed delay between activities e.g. seven days notice has to be given to users that a new release has been signed off and is to be installed
Acceptance
testing
Install new
release
20 days
1 day
7 days
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 12: Types of links between activities
Finish to start
Software
development
Acceptance testing
Start to start/ Finish to finish
Document
Amendments
Test prototype
1 day
2 days
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 13: Types of links between activities
Start to finish
Acceptance test
of new system
Cutover to new
system
Operate temporary
system
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 14: Start and finish times
Activity ‘write report software’
Earliest start (ES)
Earliest finish (EF) = ES + duration
Latest finish (LF) = latest task can be completed without affecting project end Latest start = LF - duration
activity
1 day
Earliest start
Latest finish
Latest start
Earliest finish
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 15: Example
earliest start = day 5
latest finish = day 30
duration = 10 days
earliest finish = ?
latest start = ?
Float = LF - ES - duration
What is it in this case?
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 16: ‘Day 0’
Note that in the last example, day numbers used rather than actual dates
Makes initial calculations easier – not concerned with week-ends and public holidays
For finish date/times Day 1 means at the END of Day 1.
For a start date/time Day 1 also means at the END of Day 1.
The first activity therefore begin at Day 0 i.e. the end of Day 0 i.e. the start of Day 1
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 17
Earliest start | Duration | Earliest finish
Activity label, activity description |  | 
Latest start | Float | Latest finish
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 18: Complete for the previous example
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 19: Forward pass
Start at beginning (Day 0) and work forward following chains.
Earliest start date for the current activity = earliest finish date for the previous
When there is more than one previous activity, take the latest earliest finish
EF = day 7
EF = day 10
ES = day 10
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 20: Example of an activity network
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 21: Complete the table
Activity | ES | duration | EF
A |  |  | 
B |  |  | 
C |  |  | 
D |  |  | 
E |  |  | 
F |  |  | 
G |  |  | 
H |  |  | 
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 22: Backward pass
Start from the last activity
Latest finish (LF) for last activity = earliest finish (EF)
work backwards
Latest finish for current activity = Latest start for the following
More than one following activity - take the earliest LS
Latest start (LS) = LF for activity - duration
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 23: Example: LS for all activities?
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 24: Complete the table
Activity | ES | DUR | EF | LS | LF
A |  |  |  |  | 
B |  |  |  |  | 
C |  |  |  |  | 
D |  |  |  |  | 
E |  |  |  |  | 
F |  |  |  |  | 
G |  |  |  |  | 
H |  |  |  |  | 
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 25: Float
Float = Latest finish –
Earliest start –
Duration
activity
ES
LF
Latest start
Earliest finish
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 26: Complete the table
Act-ivity | ES | DUR | EF | LS | LF | Float
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 27: Critical path
Note the path through network with zero floats
Critical path: any delay in an activity on this path will delay whole project
Can there be more than one critical path?
Can there be no critical path?
Sub-critical paths
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course

## Slide 28: Free and interfering float
B can be up to 3 days late and not affect any other activity = free float
B can be a further 2 days late – affects D but not the project end date = interfering float
0 | 7W | 7
A |  | 
2 | 2 | 9
0 | 4W | 4
B |  | 
5 | 5 | 9
0 | 10W | 10
A |  | 
0 | 0 | 10
7 | 1W | 8
D |  | 
9 | 2 | 10
10 | 2W | 12
E |  | 
10 | 0 | 12
Notes: Topics covered
Professional software development
  What is meant by software engineering.
Software engineering ethics
  A brief introduction to ethical issues that affect software engineering.
Suggested student projects
  A brief introduction to each suggested project that can be carried out by students for this course